# SNAPFLECT ASSESSMENT PORTAL

# 020_DEVELOPMENT_SPRINT_MASTER_PLAN

## Version 1.0

### Status: APPROVED BASELINE

### Master Delivery Roadmap

# DOCUMENT INFORMATION

| Field | Value |
| --- | --- |
| Document Name | Development Sprint Master Plan |
| Version | 1.0 |
| Status | FINAL |
| Purpose | Development Execution Roadmap |
| Development Model | Agile Sprint Based |
| Architecture | Modular Monolith |
| Technology | Laravel 12 + Angular 20 + MySQL 8 |

# 1. EXECUTIVE SUMMARY

This document defines:

Development Sequence

Sprint Plan

Epic Mapping

Dependency Matrix

Testing Strategy

Release Strategy

Go-Live Roadmap

This is the governing roadmap for:

Cursor AI

ChatGPT

Developers

QA Team

UAT Team

Project Management

# 2. DELIVERY PRINCIPLES

## Principle 1

Build In Dependency Order

Foundation First

## Principle 2

Vertical Slice Delivery

Every Sprint Must Deliver:

Database

Backend APIs

Frontend Screens

Tests

Documentation

## Principle 3

Production Ready Increments

Every sprint must leave platform deployable.

# 3. MASTER EPIC INVENTORY

## EPIC 01

Platform Security

Authentication

Authorization

RBAC

Users

Sessions

## EPIC 02

Governance

Organizations

Departments

Business Units

Locations

## EPIC 03

Question Bank

Questions

Categories

Tags

Difficulty Levels

## EPIC 04

Assessment Builder

Sections

Assessments

Templates

Publishing

## EPIC 05

Assessment Execution

Assignments

Attempts

Answers

Submission

## EPIC 06

Evaluation

Auto Scoring

Manual Scoring

Results

## EPIC 07

Certification

Certificates

Verification

Revocation

## EPIC 08

Notifications

Email

SMS

In-App

## EPIC 09

Analytics

Dashboards

KPIs

Reports

## EPIC 10

Integrations

Imports

Exports

Webhooks

Audit

## EPIC 11

Operations

Schedulers

Monitoring

Health

## EPIC 12

AI Proctoring

Sessions

Evidence

Reviews

## EPIC 13

Billing

Plans

Subscriptions

Invoices

Payments

# 4. SPRINT STRUCTURE

Sprint Length

2 Weeks

Sprint Capacity

80–120 Story Points

Sprint Deliverables

Code

Tests

Swagger

Documentation

Review

# 5. SPRINT 01

Platform Foundation

Duration

2 Weeks

Modules

Security

Governance

Deliverables

JWT Authentication

Users

Roles

Permissions

Organizations

Departments

RBAC Middleware

Dependencies

None

Exit Criteria

Login Working

Authorization Working

Multi-Tenancy Working

# 6. SPRINT 02

Question Bank

Modules

Question Bank

Question Categories

Question Metadata

Deliverables

Question CRUD

Question Import

Question Versioning

Dependencies

Sprint 01

# 7. SPRINT 03

Assessment Builder

Modules

Sections

Assessments

Templates

Deliverables

Assessment Designer

Publishing

Version Control

Dependencies

Sprint 02

# 8. SPRINT 04

Assessment Assignment

Modules

Assignments

Candidate Allocation

Deliverables

Assignment Engine

Assignment Notifications

Dependencies

Sprint 03

# 9. SPRINT 05

Assessment Execution

Modules

Attempts

Answers

Timers

Deliverables

Assessment Player

Save Progress

Submit Attempt

Dependencies

Sprint 04

# 10. SPRINT 06

Evaluation Engine

Modules

Scoring

Evaluation

Results

Deliverables

Auto Scoring

Manual Evaluation

Result Calculation

Dependencies

Sprint 05

# 11. SPRINT 07

Certification

Modules

Certificates

Verification

Deliverables

Certificate Generation

QR Verification

Revocation

Dependencies

Sprint 06

# 12. SPRINT 08

Notification Platform

Modules

Email

SMS

In-App

Deliverables

Templates

Queue

Delivery Tracking

Dependencies

Sprint 07

# 13. SPRINT 09

Analytics

Modules

Dashboards

KPIs

Reports

Deliverables

Executive Dashboard

Operational Dashboard

Exports

Dependencies

Sprint 08

# 14. SPRINT 10

Integrations

Modules

Imports

Exports

Webhooks

Audit

Deliverables

Webhook Engine

Audit Search

Compliance Reports

Dependencies

Sprint 09

# 15. SPRINT 11

Platform Operations

Modules

Schedulers

Monitoring

Health

Announcements

Deliverables

Health Dashboard

Scheduled Jobs

System Monitoring

Dependencies

Sprint 10

# 16. SPRINT 12

AI Proctoring Foundation

Modules

Proctoring Sessions

Evidence Capture

Deliverables

Session Tracking

Evidence Storage

Detection Pipeline

Dependencies

Sprint 11

# 17. SPRINT 13

AI Review Workbench

Modules

Detections

Reviews

Violations

Deliverables

Reviewer Console

Risk Scoring

Violation Workflow

Dependencies

Sprint 12

# 18. SPRINT 14

Billing Foundation

Modules

Plans

Subscriptions

Deliverables

Subscription Lifecycle

Plan Management

Dependencies

Sprint 13

# 19. SPRINT 15

Billing Completion

Modules

Invoices

Payments

Deliverables

Invoice Engine

Payment Tracking

Dependencies

Sprint 14

# 20. SPRINT 16

Platform Hardening

Modules

All Modules

Deliverables

Security Review

Performance Review

Architecture Review

Refactoring

Dependencies

All Previous Sprints

# 21. DEPENDENCY MATRIX

Security
    ↓

Governance
    ↓

Question Bank
    ↓

Assessment Builder
    ↓

Assignment Engine
    ↓

Assessment Execution
    ↓

Evaluation
    ↓

Certification
    ↓

Notifications
    ↓

Analytics
    ↓

Integrations
    ↓

Operations
    ↓

AI Proctoring
    ↓

Billing

# 22. QA STRATEGY

Every Sprint Must Include

Unit Tests

Feature Tests

API Tests

Security Tests

Coverage Target

80%+

# 23. UAT STRATEGY

## Cycle 1

Internal Team

## Cycle 2

Pilot Customer

## Cycle 3

Production Readiness

Acceptance Criteria

Business Approved

QA Approved

Architecture Approved

# 24. RELEASE PLAN

## Release 1

MVP

Security

Governance

Questions

Assessments

Execution

Evaluation

Target

End Sprint 06

## Release 2

Certification + Notifications

Certification

Notifications

Target

End Sprint 08

## Release 3

Analytics + Integrations

Analytics

Audit

Webhooks

Exports

Target

End Sprint 10

## Release 4

Operations + AI Proctoring

Monitoring

Health

Proctoring

Target

End Sprint 13

## Release 5

Commercial Release

Billing

Subscriptions

Payments

Target

End Sprint 15

# 25. CURSOR AI EXECUTION MODEL

For Every Sprint

Generate Models

Generate Repositories

Generate DTOs

Generate Services

Generate Policies

Generate Controllers

Generate Tests

Generate Swagger

# 26. CHATGPT GOVERNANCE MODEL

ChatGPT Reviews

Architecture

Security

Performance

Refactoring

Code Quality

Compliance

# 27. GO-LIVE CHECKLIST

Required

All APIs Complete

All Screens Complete

All Tests Passing

80% Coverage

Security Review Complete

Performance Review Complete

Backups Verified

Monitoring Enabled

Audit Enabled

# 28. PROJECT COMPLETION DEFINITION

Platform Considered Complete When

All 13 Epics Delivered

All 16 Sprints Delivered

All OpenAPI Modules Implemented

Production Deployment Successful

UAT Approved

Go-Live Approved

# 29. IMPLEMENTATION GOVERNANCE

Source Documents

PRD

ERD

001–012 Schemas

013 Architecture

014 API Architecture

015 Screen Inventory

016 RBAC

017A–017K OpenAPI

018 Implementation Plan

019 Coding Standards

020 Sprint Plan

All future development must comply.

# APPROVAL STATUS

Document

020_DEVELOPMENT_SPRINT_MASTER_PLAN

Version

v1.0

Status

APPROVED

BASELINE FROZEN

IMPLEMENTATION ROADMAP ACTIVE

CURSOR READY

DEVELOPMENT READY

# NEXT STRATEGIC STEP

Proceed to:

021_CURSOR_AI_DEVELOPMENT_PLAYBOOK v1.0

Coverage

Exact Cursor Prompts

Code Generation Workflow

Review Workflow

Refactoring Workflow

Bug Fix Workflow

Sprint Execution Templates

Developer Operating Procedures

This will become the day-to-day operating manual that you will actually use while building Snapflect with Cursor AI.

END OF DOCUMENT