# SNAPFLECT ASSESSMENT PORTAL

# 084_SPRINT_05_IMPLEMENTATION_PLAN_v1.0

Version: 1.0
Status: APPROVED IMPLEMENTATION PLAN
Sprint: Sprint 05
Module: Frontend Portal & Analytics Platform

# 1. PURPOSE

This document defines the official implementation roadmap for Sprint 05.

It transforms the approved architecture into executable development phases while maintaining the same governance model successfully used in:

Sprint 01

Sprint 02

Sprint 03

Sprint 04

# 2. SPRINT OBJECTIVE

Build the complete Angular 20 enterprise frontend that consumes all backend APIs delivered across Sprints 01–04.

Deliver:

Administration Portal

Candidate Portal

Assessment Management UI

Assessment Delivery UI

Results Portal

Reporting Dashboard

Analytics Dashboard

Certificate Foundation

# 3. IMPLEMENTATION PRINCIPLES

Mandatory:

Angular 20

Standalone Components

Signals

Lazy Loading

Reactive Forms

Angular Material

Strict TypeScript

Forbidden:

NgModules

Template Driven Forms

Direct API Calls from Components

Business Logic in Components

# 4. DEVELOPMENT STRATEGY

Sprint 05 follows a layered frontend approach:

Foundation

↓

Layout

↓

Authentication

↓

Administration

↓

Assessment

↓

Delivery

↓

Results

↓

Reporting

↓

Analytics

↓

Certificates

↓

Testing

# 5. EXECUTION PHASES

Phase 1
Frontend Foundation

Phase 2
Layout Framework

Phase 3
Authentication Module

Phase 4
Governance Module

Phase 5
Assessment Module

Phase 6
Delivery Module

Phase 7
Results Module

Phase 8
Reporting & Analytics

Phase 9
Certificate Module

Phase 10
Frontend Testing

Phase 11
Sprint Completion

# 6. PHASE 1

## FRONTEND FOUNDATION

Objective:

Create Angular application architecture.

Deliverables:

Angular 20 Project

Folder Structure

Core Module

Shared Module

Environment Configuration

Routing Foundation

Signal Stores

API Layer

Interceptors

Guards

Files:

app/core

app/shared

app/layout

app/features

Exit Criteria:

Application Compiles

Routing Works

Authentication Context Ready

# 7. PHASE 2

## LAYOUT FRAMEWORK

Objective:

Create reusable UI shell.

Deliverables:

Admin Layout

Candidate Layout

Top Navigation

Sidebar

Breadcrumb

Notifications

Footer

Exit Criteria:

Responsive Layout Ready

Role Menus Working

# 8. PHASE 3

## AUTHENTICATION MODULE

Consumes:

Sprint 01 APIs

Deliverables:

Login

Logout

Forgot Password

Reset Password

Profile

Change Password

Stores:

AuthStore

UserStore

Exit Criteria:

User Login Successful

Role Loading Successful

# 9. PHASE 4

## GOVERNANCE MODULE

Consumes:

Sprint 01 APIs

Deliverables:

Organizations

Departments

Roles

Permissions

Users

Pages:

List

Create

Edit

Detail

Exit Criteria:

Full CRUD Operational

# 10. PHASE 5

## ASSESSMENT MODULE

Consumes:

Sprint 02 APIs

Deliverables:

Assessments

Question Banks

Questions

Competencies

Blueprint Designer

Publishing

Special Deliverable:

Blueprint Visual Designer

Exit Criteria:

Assessment Lifecycle Operational

# 11. PHASE 6

## DELIVERY MODULE

Consumes:

Sprint 03 APIs

Deliverables:

Candidate Dashboard

Sessions

Attempts

Question Navigation

Timer

Answer Submission

Auto Save

Critical Components:

QuestionNavigator

AttemptTimer

ProgressTracker

AnswerPanel

Exit Criteria:

Candidate Can Complete Assessment

# 12. PHASE 7

## RESULTS MODULE

Consumes:

Sprint 04 APIs

Deliverables:

Results Dashboard

Result Details

Competency Breakdown

Version History

Publication Status

Exit Criteria:

Candidate Can View Results

Admins Can Review Results

# 13. PHASE 8

## REPORTING & ANALYTICS

Consumes:

Sprint 04 Reporting APIs

Deliverables:

Assessment Reports

Competency Reports

Pass Fail Reports

Candidate Reports

Analytics Dashboard

Charts:

Bar

Line

Pie

Donut

Heatmap

Library:

ApexCharts

Exit Criteria:

Reports Render Successfully

Charts Render Successfully

# 14. PHASE 9

## CERTIFICATE MODULE

Objective:

Create certificate foundation.

Deliverables:

Certificate List

Certificate Viewer

Certificate Download

Certificate Verification

Exit Criteria:

Certificate Workflow Operational

# 15. PHASE 10

## FRONTEND TESTING

Testing Types:

Unit Tests

Component Tests

Guard Tests

Store Tests

Integration Tests

Coverage Areas:

Authentication

Navigation

Assessment Flow

Delivery Flow

Results Flow

Reporting Flow

Exit Criteria:

Critical Paths Tested

# 16. PHASE 11

## SPRINT COMPLETION

Deliverables:

Sprint Completion Report

Release Notes

Architecture Validation

Deployment Checklist

# 17. COMPONENT INVENTORY

Estimated Components:

60–80 Standalone Components

Examples:

Data Tables

Forms

Cards

Charts

Dialogs

Dashboard Widgets

# 18. PAGE INVENTORY

Estimated Pages:

40–50 Pages

Across:

Governance

Assessment

Delivery

Results

Reporting

Certificates

# 19. STORE INVENTORY

Required Stores:

AuthStore

UserStore

NavigationStore

AssessmentStore

DeliveryStore

ResultsStore

ReportingStore

# 20. API SERVICE INVENTORY

Required Services:

AuthApiService

GovernanceApiService

AssessmentApiService

DeliveryApiService

ResultsApiService

ReportingApiService

AnalyticsApiService

CertificateApiService

# 21. DEVELOPMENT RULES

Components:

UI Only

Facades:

Business Orchestration

Stores:

State Management

API Services:

HTTP Communication

# 22. PERFORMANCE REQUIREMENTS

Mandatory:

Lazy Loading

Signals

OnPush

TrackBy

Code Splitting

Target:

Initial Bundle < 500 KB

# 23. SECURITY REQUIREMENTS

Mandatory:

Route Guards

Role Guards

Permission Guards

Session Expiry

401 Handling

403 Handling

# 24. ACCESSIBILITY REQUIREMENTS

Target:

WCAG 2.1 AA

Requirements:

Keyboard Support

ARIA Labels

Focus States

Screen Reader Support

# 25. RESPONSIVE REQUIREMENTS

Supported:

Desktop

Laptop

Tablet

Mobile

# 26. DEVELOPMENT ESTIMATE

| Phase | Area | Estimate |
| --- | --- | --- |
| 1 | Foundation | 4 Days |
| 2 | Layout | 3 Days |
| 3 | Authentication | 3 Days |
| 4 | Governance | 5 Days |
| 5 | Assessment | 8 Days |
| 6 | Delivery | 6 Days |
| 7 | Results | 4 Days |
| 8 | Reporting & Analytics | 5 Days |
| 9 | Certificates | 2 Days |
| 10 | Testing | 5 Days |
| 11 | Completion | 1 Day |

# 27. TOTAL ESTIMATE

46 Person Days

# 28. IMPLEMENTATION RISKS

## Risk 1

Blueprint Designer Complexity

Mitigation:

Component Isolation

## Risk 2

Assessment Delivery UX

Mitigation:

Dedicated Candidate Layout

## Risk 3

Reporting Performance

Mitigation:

Server-Side Pagination

# 29. GO / NO-GO CHECKLIST

Before implementation:

Architecture Approved

UI Standards Approved

Module Schema Approved

API Mapping Approved

All must be approved.

# 30. FINAL EXECUTION ORDER

079_SPRINT_05_EXECUTION_PACKAGE_v1.0

↓

080_FRONTEND_ARCHITECTURE_v1.0

↓

081_UI_UX_STANDARDS_v1.0

↓

082_FRONTEND_MODULE_SCHEMA_v1.0

↓

083_FRONTEND_OPENAPI_MAPPING_v1.0

↓

084_SPRINT_05_IMPLEMENTATION_PLAN_v1.0

↓

085_SPRINT_05_READINESS_REVIEW

↓

Implementation Begins

# 31. SUCCESS CRITERIA

Sprint 05 succeeds when:

All Modules Delivered

All APIs Consumed

RBAC Operational

Candidate Flow Operational

Reporting Operational

Certificates Operational

Responsive Design Operational

# 32. FINAL APPROVAL

084_SPRINT_05_IMPLEMENTATION_PLAN_v1.0

Status:
APPROVED

Next:
085_SPRINT_05_READINESS_REVIEW